## Team
The Team
CSC318: Software Engineering Principles
Tetris Clone
Name | Role
Christopher Koon | Product Owner
Nathan Scott | Scrum Master
Jordan Brown | Developer
Samael Newgate | Developer

## Product Backlog
Product Backlog
CSC318: Software Engineering Principles
Tetris Clone
Time Spent
Task ID | Task | Sprint Number | Priority | Start Date | End Date | Time Estimate | Sprint 1 | Sprint 2 | Sprint 3 | Total | Status | Member Assigned | Member Assigned | Member Assigned | Member Assigned
1 | As a developer, I want to research the SFML library and Tetris gameplay loop. | 1 | 1 | 2019-02-04 | 2019-02-23 | 42 | 42 | 0 | 0 | 42 | Done | Christopher Koon | Nathan Scott | Samael Newgate | Jordan Brown | x
2 | As a developer, I want to build the main gameplay loop to include, shapes, boards, spawners, scores, gravity and line destruction. | 1 & 2 | 1 | 2019-02-04 | 2019-03-14 | 74 | 49 | 23 | 0 | 72 | Done | Christopher Koon | Nathan Scott | Samael Newgate | Jordan Brown | x
3 | As a developer, I want to create a graphical user interface for the menus, game pieces, sprites, backgrounds and buttons. | 2 & 3 | 2 | 2019-02-25 | 2019-03-14 | 60 | 0 | 52 | 10 | 62 | Done | Christopher Koon | Nathan Scott | Jordan Brown | Samael Newgate
4 | As a developer, I would like to polish the end project with QA, difficulty increasing algorithms, and final asset implementation. | 3 | 3 | 2019-03-25 | 2019-04-11 | 27 | 0 | 8 | 33 | 8 | Done | Christopher Koon | Nathan Scott | Jordan Brown | Samael Newgate
[ - ] | Completed Product | Final | [ - ] | 2019-02-04 | 2019-04-11 | 203 | 91 | 102 | 43 | 217 | Done | All Members | All Members | All Members | All Members

## Sprint 1 Backlog
Sprint 1 Backlog
CSC318: Software Engineering Principles
Tetris Clone
Time Spent
Item Number | Task | Sprint Number | Priority | Start Date | Time Estimate | Week 1 | Week 2 | Week 3 | Total | Status | Member Assigned
2.1 | Shape Class Creation | 1 | 1 | 2019-02-05 | 20 | 3 | 6 | 10 | 19 | Done | Jordan Brown | Nathan Scott | Not Assigned | Not Assigned
2.2 | Board Class Creation | 1 | 2 | 2019-02-11 | 12 | 0 | 8 | 4 | 12 | Done | Jordan Brown | Samael Newgate | Nathan Scott | Not Assigned
2.3 | Shape Spawner Creation | 1 | 3 | 2019-02-11 | 10 | 0 | 6 | 4 | 10 | Done | Jordan Brown | Samael Newgate | Nathan Scott | Not Assigned
1.2 | Research SFML graphics programming | 1 | 4 | 2019-02-05 | 22 | 0 | 8 | 13 | 21 | Done | Christopher Koon | Samael Newgate | Nathan Scott | Not Assigned
1.1 | Research Tetris Gameplay Loop | 1 | 5 | 2019-02-05 | 20 | 14 | 9 | 0 | 23 | Done | Christopher Koon | Samael Newgate | Jordan Brown | Nathan Scott
[ - ] | Completed Sprint | [ - ] | [ - ] | 2019-02-05 | 84 | 16 | 26 | 22 | 85 | Done | All Members | All Members | All Members | All Members

## Sprint 2 Backlog
Sprint 2 Backlog
CSC318: Software Engineering Principles
Tetris Clone
Time Spent
Item Number | Task | Sprint Number | Priority | Start Date | Time Estimate | Week 1 | Week 2 | Week 3 | Total | Status | Member Assigned
2.6 | Create Artificial Gravity for blocks falling | 2 | 1 | 2019-02-25 | 8 | 2 | 4 | 0 | 8 | Done | Jordan Brown | Not Assigned | Not Assigned | Not Assigned
2.5 | Destroyable Lines when row filled | 2 | 2 | 2019-02-25 | 4 | 0 | 4 | 3 | 10 | Done | Jordan Brown | Nathan Scott | Not Assigned | Not Assigned
2.7 | Create gameplay loop start and ending | 2 | 3 | 2019-03-03 | 15 | 0 | 6 | 6 | 14 | Done | Jordan Brown | Nathan Scott | Not Assigned | Not Assigned
2.4 | Score Creation | 1 | 4 | 2019-02-25 | 5 | 3 | 5 | 2 | 10 | Done | Samael Newgate | Not Assigned | Not Assigned | Not Assigned
3.1 | Create Sprites for pieces, border and background | 2 | 5 | 2019-02-25 | 30 | 8 | 10 | 4 | 22 | Done | Christopher Koon | Not Assigned | Not Assigned | Not Assigned
4.3 | Increment difficulty based on lines cleared | 3 | 4 | 2019-03-03 | 8 | 0 | 5 | 4 | 8 | Done | Jordan Brown | Not Assigned | Not Assigned | Not Assigned | * Added
3.2 | Implement graphics using SFML library, to include pieces, board, and background. | 3 | 3 | 2019-03-03 | 30 | 0 | 14 | 16 | 30 | Done | Samael Newgate | Christopher Koon | Not Assigned | Not Assigned | * Added
[ - ] | Completed Sprint | [ - ] | [ - ] | 2019-02-25 | 62 | 13 | 48 | 35 | 102 | Done | All Members | All Members | All Members | All Members

## Sprint 3 Backlog
Sprint 3 Backlog
CSC318: Software Engineering Principles
Tetris Clone
Time Spent
Item Number | Task | Sprint Number | Priority | Start Date | Time Estimate | Week 1 | Week 2 | Week 3 | Total | Status | Member Assigned
4.1 | Save & Read Scores to disk | 3 | 1 | 2019-03-25 | 7 | 5 | 2 | 0 | 7 | Done | Nathan Scott | Not Assigned | Not Assigned | Not Assigned
4.2 | Create Selectable Difficulty 1 through 10, higher difficulty means blocks fall faster | 3 | 2 | 2019-03-25 | 12 | 6 | 3 | 0 | 9 | Done | Jordan Brown | Not Assigned | Not Assigned | Not Assigned
4.3 | Main Menu Asset Creation | 3 | 3 | 2019-03-25 | 5 | 5 | 0 | 0 | 5 | Done | Christopher Koon | Not Assigned | Not Assigned | Not Assigned
4.4 | Button Asset Creation | 3 | 3 | 2019-03-25 | 5 | 0 | 5 | 0 | 5 | Done | Christopher Koon | Not Assigned | Not Assigned | Not Assigned
4.5 | Main Menu Implementation | 3 | 4 | 2019-04-01 | 15 | 0 | 7 | 10 | 17 | Done | Samael Newgate | Christopher Koon | Not Assigned | Not Assigned
[ - ] | Completed Sprint | [ - ] | [ - ] | 2019-03-25 | 44 | 16 | 17 | 10 | 43 | Done | All Members | All Members | All Members | All Members

## Resources
Status | Team Members
Done | Christopher Koon
Ongoing | Nathan Scott
Planned | Samael Newgate
Removed | Jordan Brown
All Members
Not Assigned